## gather-sprint-planni
Gather: Sprint Planning
Week 4
Name | Subitems | Person | Status | Priority | Estimation | Description | Creation Log
Introductory Partner Call |  | utku | Done | High | 1 |  | utku Nov 18, 2021 02:42 PM
Github Repo Setup |  | utku | Done | High | 1 |  | utku Nov 18, 2021 02:42 PM
Scoping of the project |  | utku, roxana, roland | Done | High | 5 |  | utku Nov 18, 2021 02:42 PM
7
Week 5 - 6
Name | Subitems | Person | Status | Priority | Estimation | Description | Creation Log
Explore Data Sources | Sentinel-2, OpenStreetMap, Overpass API | utku | Done | High | 13 |  | utku Nov 18, 2021 02:49 PM
Subitems | Name | Owner | Status | Description
| Sentinel-2 | utku | Done
| OpenStreetMap | utku | Done
| Overpass API | utku | Done
Literature review |  | roland | Done | High | 8 |  | utku Nov 18, 2021 02:51 PM
Project Roadmap Meeting with the partner |  | utku, roxana, roland | Done | Medium | 1 |  | utku Nov 18, 2021 03:23 PM
22
Week 7 - 8
Name | Subitems | Person | Status | Priority | Estimation | Description | Creation Log
Pretrained models |  | roland, roxana | Done | High | 8 |  | utku Nov 18, 2021 02:51 PM
Google Maps API |  | roxana | Done | High | 5 |  | utku Dec 2, 2021 02:39 PM
More literature |  | roland | Done | Medium | 5 |  | utku Dec 2, 2021 02:53 PM
Functions to get osm linestrings |  | utku | Done | High | 5 |  | utku Jan 26, 2022 02:39 PM
23
Week 9 - 10
Name | Subitems | Person | Status | Priority | Estimation | Description | Creation Log
Interim Presentation |  | utku, roland, roxana | Done | High | 5 |  | utku Dec 2, 2021 02:40 PM
Combine osm lines to images |  | utku | Done | High | 8 |  | utku Dec 2, 2021 02:41 PM
13
Week 11 - 12
Name | Subitems | Person | Status | Priority | Estimation | Description | Creation Log
Create labeled training set |  | utku | Done | High | 8 |  | roland Dec 16, 2021 10:28 AM
Clean the code and update github |  | utku, roland, roxana | Done | High | 3 |  | roland Dec 16, 2021 10:32 AM
CI/CD pipeline |  | roxana | Stuck | Medium | 8 |  | utku Jan 26, 2022 02:16 PM
search for annotation tools |  | roland, utku | Done | Medium | 5 |  | roland Jan 27, 2022 10:15 AM
24
Week 13 - 14
Name | Subitems | Person | Status | Priority | Estimation | Description | Creation Log
Check SMA Road Network |  | utku | Done | Medium | 2 |  | utku Dec 2, 2021 02:41 PM
Alternative data sources |  | utku | Done | Medium | 5 |  | utku Nov 18, 2021 02:52 PM
Get image&mask dataset |  | utku | Done | High | 8 |  | utku Feb 8, 2022 10:05 AM
15
Week 15 - 16
Name | Subitems | Person | Status | Priority | Estimation | Description | Creation Log
Train a new model | Tuning, Connect to LRZ | utku | Done | High | 13 |  | utku Feb 8, 2022 10:44 AM
Subitems | Name | Owner | Status | Description
| Connect to LRZ | utku | Blocked
| Tuning | utku | Done
Evaluation metric |  | utku | Done | High | 5 |  | utku Feb 8, 2022 05:27 PM
Re-train the model |  | roland | Done | High | 8 |  | utku Jan 26, 2022 02:15 PM
26
Week 17 - 18
Name | Subitems | Person | Status | Priority | Estimation | Description | Creation Log
Final presentation |  | utku, roland | Done | High | 8 |  | utku Feb 11, 2022 05:57 PM
8
Week 19 - 20
Name | Subitems | Person | Status | Priority | Estimation | Description | Creation Log
Deliverables |  | utku, roland | Done | High | 13 |  | utku Feb 11, 2022 06:03 PM
13
Backlog
Name | Subitems | Person | Status | Priority | Estimation | Description | Creation Log
Alternative performance measures | [6 empty] | utku Nov 18, 2021 02:51 PM
Handling false positives | [6 empty] | utku Dec 2, 2021 02:42 PM
Create Test Infrastructure | [6 empty] | roland Dec 16, 2021 10:29 AM
Documentation github pages | [6 empty] | utku Feb 10, 2022 11:18 AM
Deployment | [6 empty] | utku Feb 10, 2022 11:19 AM
0